## Action Plan
Goal #1
Strengthen our Academic Programs, including General Education, to ensure they are current, distinctive and mission driven.
Dean sponsor | Richard Cavaletto
Leaders | Peter Livingston
Leanne Berning
1 | SUB-GOAL 1: Evaluate GE offerings by department
# | Action | Status | Next Steps | Owner of Next Steps | Comments
1 | Complete required course submissions to convert old Area F courses to new GE courses
2 | Modify GE courses as necessar to ensure they generate at least 30 SCU/WTU
3 | Develop five (5) new GE courses in areas such as B, D4, D5, etc.
4
2 | SUB-GOAL 2: Determine which majors/programs will grow over the next three to five years using student demand and job trend data
# | Action | Status | Next Steps | Owner of Next Steps | Comments
1 | Determine data needed and collect
2 | Review literature and employment reports
3 | Identify metrics to evaluate potential majors
4 | Test Case #1
5 | Test Case #2
3 | SUB-GOAL 3: Develop and truth case statement for at least two (2) potential new college majors.
# | Action | Status | Next Steps | Owner of Next Steps | Comments
1 | Gather historical data showing applicant demand trends over past five years for each major | Marnie gathering data | Richard to review and verify data; adjust as needed | Richard
2 | Convene task force members |  | Richard to work with Jacquie to review calendars and schedule meeting | Richard/Jacquie
3 | Distribute 1) applicant trend data, 2) Advance and 3) Fall Conference breakout notes to task force for review/refresh |  | Richard and Jacquie to gather all relevant materials and send to task force | Richard/Jacquie
4
5

## goal2
Goal #2
Enrich the campus culture of diversity, equity and inclusion
Dean Sponsor | Richard Cavaletto
Leaders | Stephanie Jung
Ann De Lay
Sub Goals and Tactics |  | Status | Next Steps | Owner of Next Steps | Comments
Continue CAFES DEI program established in 2018-19 by planning and executing at least four events throughout the academic year: workshops, high-profile guest speakers, Aspire to Grow conference, etc. |  | (Details listed in khaki below)
Trainings/Workshops |  | Cultural Intelligence (CQ) Assessment and Training of CAFES faculty and staff during 2019 Fall Conference with Justin Gomez; CAFES DEI Committee members have been tasked with working with their individual departments and units to encourage faculty and staff to complete the Development Plan at the back of their CQ reports (fall 2019). CAFES DEI committee is working with the Dean's Office to secure a date for a second training for those unable to attend the previous session (likely winter 2020). For students, Fresh Perspectives is again being offered through CAFES clubs with representation at the CAFES Council. The Latinos in Agriculture (LIA) club is again hosting 26 Hours in March, an event sponsored by the CAFES. | During winter quarter 2020 the CAFES DEI Committee will identify a series of topics based on the CQ report, the CPx results and CAFES-specific CPx report in order to plan a college-wide event during spring 2020. | CAFES DEI Committee, Ann De Lay, LIA | Fresh Perspectives will feature three modules for clubs for the 2019-2020 year. LIA will begin planning 26 Hours beginning in January 2020.
High-profile guest speakers |  | Industry leaders will be participating in Aspire to Grow, through keynotes and panel discussions. | Winter quarter 2020, the CAFES DEI Committee will be working to identify a single speaker to come to campus for a day to (1) engage with student groups and (2) speak at a late afternoon/early evening event. Speaking event to be hosted spring quarter. | CAFES DEI Committee | What is the budget for an invited speaker?
Aspire to Grow conference |  | Speakers and sponsors are currently being identified by the planning committee. | Participation to be finalized early winter quarter. Event to take place March 3, 2020 in the PAC. | Haley Marconett, Donna Packard, Ann De Lay, Gissel Neri-Corcoles, and Emma Mannoukian
Lunch and Learns/Brown Bag |  | CAFES DEI met to discuss the potential for Lunch and Learns/Brown Bags within the College. There was great interest and members will take turns hosting sessions during winter 2020 and spring 2020 quarters. Winter quarter dates include: 1/23 (Diversity Speaker Series viewing party) and 2/20 (topic to be determined). Content for future sessions could include: TedTalk, read an article, expert speaker, open dialogue. Goal is to meet twice per quarter. | Have communicated with Dr. Oscar Navarro (SOE) to host a session in spring quarter. Will visit with Sarah Macdonald (1/24) to identify additional content. Work with DEI Committee to plan calendar of topics for spring 2020. Schedule to be accomplished during winter quarter 2020. | CAFES DEI Committee
Develop and finalize governance for college DEI Committee |  | Governance document outline has been developed and presented to the CAFES DEI Committee at the November 2019 meeting. Furthermore, language regarding the full integration of staff and student committee members has been added. | The CAFES DEI committee will be working on document revisions through, winter 2020. Seeking to finalize in March, 2020. | CAFES DEI Committee | This document seeks to create clarity around the mission and structure of the CAFES Diversity, Equity, and Inclusion (DEI) Committee to ensure proper representation and administration. The document will be used at the College and Department Head level to explain to interested individuals, more about the group. The document will be featured on the CAFES website.
Communicate more broadly our achievements in DEI |  | The CAFES DEI webpage went live in September 2019 to showcase the CAFES vision, committee, events, resources, award, and more. Over summer 2019, Amy Robbins in the Provost's Office collected each College's DEI activities to share with university administrators and OUDI. This document features additional activities CAFES does beyond this strategic goal document. Activities, accomplishments and features are shared through college-level social media. Cultivate magazine and department newsletters are also featuring college DEI efforts. Additionally, the Faculty Fellow for DEI attends the OUDI meetings with all of the Associate Deans responsible for those efforts. The space allows CAFES activities to be shared across campus. CAFES DEI sent its first quarterly newsletter in December 2019, featuring work accomplished, upcoming events, and opportunities for engagement. | The CAFES DEI webpage will be updated regularly. Website feedback is constantly being sought by the CAFES DEI Committee. | CAFES DEI Committee, Haley Marconett, DH
Take appropriate action pending results of CPX Survey |  | CAFES DEI met in November 2019 and discussed the CPX results. At the time, they were awaiting the college-specific report. | CAFES DEI members and college leadership have attended CPX dialogue sessions to gain a better understanding of the reports and to learn about university initiatives to create change. The CAFES DEI committee has reviewed the reports to identify next steps for the CAFES DEI Action Plan. | CAFES DEI Committee